## Milestone1 Report
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Type Of Defect | Action Taken | Action Taken Date | Status | Remarks
1 | Mudrika Patel | 09-07-2026 | Research findings on defect analysis workflow, RAG architecture and semantic similarity techniques were not documented. | Sprint 1 | Documentation | Prepared research notes and summarized findings in project documentation and presentation. | 2026-07-02 | Closed | Research documentation completed.
2 | Mudrika Patel | 09-07-2026 | System architecture and agent workflow documentation was incomplete. | Sprint 1 | Documentation | Created system architecture diagram, module responsibilities, orchestration flow and knowledge base design. | 2026-07-02 | Closed | Design documentation completed.
3 | Mudrika Patel | 09-07-2026 | File upload module was not accepting PDF and TXT bug reports correctly. | Sprint 1 | Functional | Updated upload validation and added support for PDF and TXT file formats. | 2026-07-02 | Closed | Upload module working successfully.
4 | Mudrika Patel | 09-07-2026 | Streamlit UI layout was misaligned on smaller screen resolutions. | Sprint 1 | UI | Modified layout using Streamlit containers and responsive columns. | 2026-07-03 | Closed | Responsive UI verified.
5 | Mudrika Patel | 09-07-2026 | Uploaded log/error files generated parsing errors for unsupported content. | Sprint 1 | Functional | Added exception handling and improved file parsing logic. | 2026-07-03 | Closed | Error handling implemented successfully.
6 | Mudrika Patel | 09-07-2026 | Bug submission form accepted empty bug descriptions. | Sprint 1 | Validation | Implemented mandatory input validation before submission. | 2026-07-03 | Closed | Empty submissions are now restricted.
7 | Mudrika Patel | 09-07-2026 | Vector database indexing was not initialized during RAG knowledge base setup. | Sprint 1 | Backend | Implemented vector store initialization and indexing for the knowledge base. | 2026-07-04 | Closed | Knowledge base indexed successfully.